## Gantt
Project timeline — Generic Ice Hockey Stadium Energy Model
MATH3001 Applied Mathematical Modelling · Group 8 · Semester 2, 2026
Task | Stream | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Teaching week → |  | 3 Aug | 10 Aug | 17 Aug | 24 Aug | 31 Aug | 7 Sep | 14 Sep | 21 Sep | 28 Sep | 5 Oct | 12 Oct | 19 Oct
|  |  |  | tuition free week |  |  | mid-sem test |  |  | tuition free week
Literature review | Research | bar: 3 Aug to 7 Sep; 28 Sep
Model formulation | Modelling | bar: 10 Aug to 24 Aug; 7 Sep; 28 Sep
Governing equations | Modelling | bar: 17 Aug; 31 Aug to 14 Sep; 28 Sep
Mathematical analysis | Modelling | bar: 17 Aug; 7 Sep to 28 Sep
Numerical simulation | Implementation | bar: 17 Aug; 7 Sep; 21 Sep to 5 Oct
Interpretation of results | Implementation | bar: 17 Aug; 7 Sep; 28 Sep to 12 Oct
Report preparation | Writing | bar: 17 Aug; 7 Sep; 28 Sep to 19 Oct
Presentation preparation | Writing | bar: 17 Aug; 7 Sep; 28 Sep to 12 Oct
Submission | bar: 24 Aug; 14 Sep to 28 Sep; 12 Oct to 19 Oct
[5 empty] | Tasks 3 & 4 |  |  | Research Proposal | Progress + prelim. results | Progress Report |  | Slides | Final Report
Legend
Research
Modelling
Implementation
Writing

## Data
Task data
Task | Stream | Start week | Duration (weeks) | End week
Literature review | Research | 3 | 5 | 7
Model formulation | Modelling | 4 | 3 | 6
Governing equations | Modelling | 7 | 3 | 9
Mathematical analysis | Modelling | 9 | 2 | 10
Numerical simulation | Implementation | 10 | 3 | 12
Interpretation of results | Implementation | 12 | 2 | 13
Report preparation | Writing | 11 | 4 | 14
Presentation preparation | Writing | 12 | 2 | 13